## Sheet1
Div. | Activity | ID Serial | Activity ID Fixed Part | Successor (1) Fixed ID | Successor (1) Relationship | Successor (1) Lag | Original Duration (Default Value)
02 | Excavation Works | 1000 | 02.1000 | 02.1005 | FS | 0 | 8
02 | Anti-Termite Works | 1005 | 02.1005 | 07.1300 | FS | 0 | 1
02 | Structure backfilling under foundation level | 1010 | 02.1010 | 02.1005 | FS | 0 | 15
02 | Backfilling around foundation & neck columns | 1015 | 02.1015 | 03.1060 | FS | 0 | 12
02 | Backfilling around grade beams | 1020 | 02.1020 | 02.1025 | FS | 0 | 8
02 | Gravel layer works | 1025 | 02.1025 | 07.1305 | FS | 0 | 2
02 | Interlock Concrete Pavers | 1030 | 02.1030 |  |  |  | 6
02 | Agricultural Soil Works | 1035 | 02.1035 |  |  |  | 4
03 | Plain Concrete Works | 1040 | 03.1040 | 03.1045 | FS | 0 | 8
03 | RC Foundation Works | 1045 | 03.1045 | 03.1055 | FS | 0 | 16
03 | RC Raft Foundation Works | 1050 | 03.1050 |  |  |  | 5
03 | RC Column Necks & Walls | 1055 | 03.1055 | 07.1310 | FS | 0 | 12
03 | Grade Beams Works | 1060 | 03.1060 | 07.1315 | FS | 0 | 12
03 | PC under slab on grade | 1065 | 03.1065 |  |  |  | 4
03 | RC slab on grade works | 1070 | 03.1070 | 04.1165 | FS | 0 | 12
03 | RC Column Works | 1075 | 03.1075 | 03.1080 | SS | 0 | 16
03 | RC Concrete Walls | 1080 | 03.1080 | 03.1085 | FS | 0 | 8
03 | Concrete Slab Works | 1085 | 03.1085 |  |  |  | 20
03 | Solid Slab Works | 1090 | 03.1090 |  |  |  | 14
03 | RC Electrical ternch | 1095 | 03.1095 |  |  |  | 6
03 | RC Beam for parapet | 1100 | 03.1100 |  |  |  | 4
03 | RC Roof Parapet Wall | 1105 | 03.1105 | 03.1130 | FS | 0 | 4
03 | Ribbed Slab Works | 1110 | 03.1110 |  |  |  | 20
03 | Waffle Slab Works | 1115 | 03.1115 |  |  |  | 20
03 | Hollow Core Slab Works | 1120 | 03.1120 |  |  |  | 20
03 | Double T Slab Works | 1125 | 03.1125 |  |  |  | 18
03 | Precast parapet works | 1130 | 03.1130 | 09.1635 | FS | 0 | 6
03 | Precast Concrete Slab to cover openings | 1135 | 03.1135 |  |  |  | 5
03 | Concrete Cover for expansion joints | 1140 | 03.1140 | 05.1255 | SS | 0 | 5
03 | Screed Works | 1145 | 03.1145 |  |  |  | 4
03 | Lintels Works (cast in place) | 1150 | 03.1150 | 09.1420 | FS | 0 | 4
03 | Lintels Works (precast) | 1155 | 03.1155 | 09.1420 | FS | 0 | 4
03 | RC of Enterrance Stair | 1160 | 03.1160 |  |  |  | 6
04 | Masonary works | 1165 | 04.1165 | 03.1155 | SS | 2 | 20
04 | Stone Cladding Works for façade | 1170 | 04.1170 |  |  |  | 14
04 | Stone Cladding Works | 1175 | 04.1175 |  |  |  | 8
04 | Stone Works for decoration | 1180 | 04.1180 |  |  |  | 8
04 | Masonary works for Roof | 1185 | 04.1185 | 03.1105 | FS | 0 | 10
04 | Stone Works for Agriculture basins | 1190 | 04.1190 |  |  |  | 4
04 | Lintels and Sills installation | 1195 | 04.1195 |  |  |  | 4
05 | Aluminum shed Works | 1200 | 05.1200 |  |  |  | 5
05 | Handrail Works | 1205 | 05.1205 |  |  |  | 8
05 | Metal Handles for stairs | 1210 | 05.1210 | 05.1260 | FS | 0 | 12
05 | Metal Ladder installation | 1215 | 05.1215 |  |  |  | 6
05 | Metal Doors Intallation | 1220 | 05.1220 |  |  |  | 3
05 | Steel Structure works | 1225 | 05.1225 |  |  |  | 20
05 | Metal sheds works | 1230 | 05.1230 | 05.1260 | FS | 0 | 8
05 | Metal Ceiling works | 1235 | 05.1235 |  |  |  | 5
05 | Stainless Steel Sheets for façade | 1240 | 05.1240 |  |  |  | 10
05 | Aluminum Louver for Façade | 1245 | 05.1245 |  |  |  | 6
05 | Covers for agriculture basins | 1250 | 05.1250 |  |  |  | 2
05 | Expansion Joints covers | 1255 | 05.1255 |  |  |  | 4
05 | Metal Covers for Roofing Duct | 1260 | 05.1260 |  |  |  | 4
06 | Kitchen Cabinets Works | 1265 | 06.1265 |  |  |  | 6
06 | Wooden Cabinets | 1270 | 06.1270 | 12.1685 | FF | 0 | 6
06 | Wooden Works (Decoration) | 1275 | 06.1275 |  |  |  | 8
06 | Textile works for sound inuslation | 1280 | 06.1280 |  |  |  | 16
06 | Wooden Cladding | 1285 | 06.1285 |  |  |  | 8
06 | Dry wall wooden partitions | 1290 | 06.1290 |  |  |  | 6
06 | Wooden Treads | 1295 | 06.1295 |  |  |  | 6
07 | Polyethelene Sheets Works below blinding | 1300 | 07.1300 | 03.1040 | FS | 0 | 4
07 | Polyethelene Sheets Works below slab on grade | 1305 | 07.1305 | 03.1065 | FS | 0 | 4
07 | Waterproofing for foundations & column necks | 1310 | 07.1310 | 02.1015 | FS | 0 | 4
07 | Waterproofing for grade beams | 1315 | 07.1315 | 02.1020 | FS | 0 | 4
07 | Water proofing for wet areas | 1320 | 07.1320 | 09.1485 | FS | 0 | 6
07 | Thermal Insulation for Walls | 1325 | 07.1325 | 09.1420 | FS | 0 | 4
07 | Foam concrete for roof | 1330 | 07.1330 | 07.1335 | FS | 0 | 8
07 | Waterproofing for roof floor | 1335 | 07.1335 | 07.1355 | FS | 0 | 10
07 | Waterproofing for parapet | 1340 | 07.1340 |  |  |  | 2
07 | Gravel works for roof | 1345 | 07.1345 | 07.1360 | FS | 0 | 10
07 | Thermal insulation works for roof | 1350 | 07.1350 | 07.1345 | FS | 0 | 4
07 | Aluminum flashing for roof | 1355 | 07.1355 | 07.1350 | FS | 0 | 4
07 | Cement Tiling for Roof Works | 1360 | 07.1360 | 15.1895 | FS | 0 | 6
07 | Precast concrete tiles | 1365 | 07.1365 |  |  |  | 12
07 | Thermal insulation works | 1370 | 07.1370 |  |  |  | 6
07 | Caulking joints including backing rod | 1375 | 07.1375 | 09.1500 | FS | 0 | 4
07 | Façade Caulking joints including backing rod | 1380 | 07.1380 | 05.1260 | FS | 0 | 4
08 | Windows installation | 1385 | 08.1385 | 09.1440 | FS | 0 | 12
08 | Wooden Doors installation | 1390 | 08.1390 | 09.1445 | FS | 0 | 16
08 | Doors accessories installation | 1395 | 08.1395 |  |  |  | 6
08 | Steel Doors installation | 1400 | 08.1400 | 09.1445 | FS | 0 | 10
08 | Aluminum Doors installation | 1405 | 08.1405 |  |  |  | 2
08 | Glass Doors installation | 1410 | 08.1410 | 09.1445 | FS | 0 | 4
08 | Curtain Wall - Aluminum façade Works | 1415 | 08.1415 | 07.1380 | FS | 0 | 12
09 | Internal Plaster works | 1420 | 09.1420 | 15.1730 | FS | 0 | 20
09 | External Plaster works | 1425 | 09.1425 |  |  |  | 12
09 | Plaster for parapet | 1430 | 09.1430 |  |  |  | 14
09 | Putty Coat Works | 1435 | 09.1435 | 09.1550 | FS | 0 | 18
09 | First and Second painting coats | 1440 | 09.1440 | 09.1445 | FS | 0 | 18
09 | Final painting coat | 1445 | 09.1445 | 12.1685 | FS | 0 | 16
09 | Painting for Gypsum board ceiling | 1450 | 09.1450 |  |  |  | 14
09 | Gypsum Board Suspended Ceiling | 1455 | 09.1455 | 09.1445 | FS | 0 | 8
09 | Ceiling Tiles Works | 1460 | 09.1460 | 15.1950 | FS | 0 | 12
09 | Metal Suspended Ceiling (Aluminum strips) | 1465 | 09.1465 | 15.1950 | FS | 0 | 8
09 | Façade Painting | 1470 | 09.1470 |  |  |  | 4
09 | Ceramic tiles for Flooring works | 1475 | 09.1475 |  |  |  | 3
09 | Ceramic tiles for walls | 1480 | 09.1480 |  |  |  | 12
09 | Ceramic tiles for Wet Areas Flooring | 1485 | 09.1485 | 09.1605 | FS | 0 | 8
09 | Ceramic tiles for Wet Areas Walls | 1490 | 09.1490 | 07.1320 | FS | 0 | 10
09 | Ceramic Skirting works | 1495 | 09.1495 |  |  |  | 4
09 | Porcelain tiles for Flooring | 1500 | 09.1500 | 09.1505 | FS | 0 | 20
09 | Porcelain skrting works | 1505 | 09.1505 | 09.1570 | FS | 0 | 8
09 | Marble tiles works | 1510 | 09.1510 | 09.1520 | FS | 0 | 8
09 | Marble frames works | 1515 | 09.1515 |  |  |  | 8
09 | Marble skirting works | 1520 | 09.1520 | 09.1535 | FF | 0 | 2
09 | Decorative Marble tiles works | 1525 | 09.1525 |  |  |  | 12
09 | Granite tiles works | 1530 | 09.1530 | 09.1535 | FS | 0 | 8
09 | Granite skirting works | 1535 | 09.1535 | 05.1255 | FF | 0 | 8
09 | Marble cladding works | 1540 | 09.1540 |  |  |  | 6
09 | Granite cladding works | 1545 | 09.1545 |  |  |  | 12
09 | Granite Stairs works | 1550 | 09.1550 | 05.1210 | FS | 0 | 8
09 | Marble Stairs works | 1555 | 09.1555 |  |  |  | 4
09 | Stone Stairs works | 1560 | 09.1560 |  |  |  | 6
09 | Terrazzo tiles works | 1565 | 09.1565 | 09.1570 | FS | 0 | 4
09 | Terrazzo skirting works | 1570 | 09.1570 | 09.1520 | FF | 0 | 2
09 | Epoxy paints | 1575 | 09.1575 |  |  |  | 8
09 | Carpet Installation | 1580 | 09.1580 |  |  |  | 12
09 | Stone tiles for flooring works | 1585 | 09.1585 |  |  |  | 4
09 | Marble installation for counter | 1590 | 09.1590 |  |  |  | 6
09 | Granite installation for counter | 1595 | 09.1595 |  |  |  | 6
09 | Agriculture basins works | 1600 | 09.1600 |  |  |  | 6
09 | Counters for toilets | 1605 | 09.1605 | 10.1645 | FS | 0 | 4
09 | Mosque special works | 1610 | 09.1610 |  |  |  | 10
09 | Gypsum Board Partitions | 1615 | 09.1615 |  |  |  | 4
09 | Stone frames installation | 1620 | 09.1620 |  |  |  | 4
09 | Raised Floor installation | 1625 | 09.1625 |  |  |  | 6
09 | Colored plaster works | 1630 | 09.1630 | 08.1385 | FS | 0 | 20
09 | Colored plaster works for parapet | 1635 | 09.1635 | 09.1630 | FS | 0 | 12
09 | Marble-Granite Thresholds | 1640 | 09.1640 | 05.1255 | FS | 0 | 8
10 | Toilet Accessories and Fixtures Installation | 1645 | 10.1645 |  |  |  | 10
10 | Signage works | 1650 | 10.1650 |  |  |  | 4
10 | Vinyl Floor installation | 1655 | 10.1655 |  |  |  | 4
11 | Equipment Installation | 1660 | 11.1660 |  |  |  | 5
11 | Sliding Galvenized Steel Gate installation | 1665 | 11.1665 |  |  |  | 8
11 | Rising Step Barriers installation | 1670 | 11.1670 |  |  |  | 3
11 | Car Barriers installation | 1675 | 11.1675 |  |  |  | 14
11 | Scanner Machine installation | 1680 | 11.1680 |  |  |  | 5
12 | Furniture Installation | 1685 | 12.1685 |  |  |  | 12
14 | Elevator works-Installing Rails | 1690 | 14.1690 | 14.1695 | FS | 0 | 10
14 | Elevator works-Installing Cabin & Motor | 1695 | 14.1695 | 14.1700 | FS | 0 | 14
14 | Elevator works-Installing Accessories & Finishes | 1700 | 14.1700 |  |  |  | 8
15 | MEP Sleeves in Grade Beams | 1705 | 15.1705 | 03.1075 | FS | 0 | 4
15 | MEP Sleeves in Concrete Slab | 1710 | 15.1710 | 15.1720 | FS | 0 | 4
15 | MEP works under slab on Grade | 1715 | 15.1715 | 02.1020 | FS | 0 | 8
15 | Chipping and cutting in walls for sanitary pipes | 1720 | 15.1720 | 15.1725 | FS | 0 | 4
15 | Embeded Sanitary pipes installation | 1725 | 15.1725 | 15.1745 | FS | 0 | 8
15 | Sanitary Pipes Risers installation | 1730 | 15.1730 | 15.1990 | FS | 0 | 8
15 | Suspended Sanitary pipes installation | 1735 | 15.1735 | 15.1765 | FS | 0 | 8
15 | Valves and accessories for Drainage System | 1740 | 15.1740 | 15.1745 | FS | 0 | 4
15 | Testing Sanitary pipes | 1745 | 15.1745 | 15.1790 | FS | 0 | 2
15 | Chipping and cutting in walls for water supply pipes | 1750 | 15.1750 | 15.1755 | FS | 0 | 4
15 | Embeded Water Supply pipes installation | 1755 | 15.1755 | 15.1775 | FS | 0 | 4
15 | Water Supply Pipes Risers installation | 1760 | 15.1760 | 15.2010 | FS | 0 | 6
15 | Suspended Water Supply pipes installation | 1765 | 15.1765 | 15.1750 | FS | 0 | 6
15 | Valves and accessories for Water Supply Ststem | 1770 | 15.1770 | 15.1780 | FS | 0 | 4
15 | Testing Water Supply pipes | 1775 | 15.1775 | 15.1770 | FS | 0 | 2
15 | Electrical water heater | 1780 | 15.1780 | 09.1465 | FS | 0 | 8
15 | Floor drain main body installation | 1785 | 15.1785 | 15.1745 | FS | 0 | 4
15 | Floor drain cover installation | 1790 | 15.1790 |  |  |  | 4
15 | Clean out installation | 1795 | 15.1795 | 15.1790 | FF | 0 | 4
15 | Plumbing Fixtures Installations | 1800 | 15.1800 | 15.1790 | FF | 0 | 10
15 | Roof drain installation | 1805 | 15.1805 | 07.1330 | FS | 0 | 4
15 | Fire Fighting pipes installation | 1810 | 15.1810 | 15.1995 | FS | 0 | 12
15 | Fire Fighting pipes risers installation | 1815 | 15.1815 | 15.1990 | FS | 0 | 8
15 | Fire Fighting valves and accessories | 1820 | 15.1820 | 15.1835 | FS | 0 | 6
15 | Fire-hose cabintes installation | 1825 | 15.1825 | 09.1445 | FS | 0 | 10
15 | Fire extinguishers installation | 1830 | 15.1830 |  |  |  | 8
15 | Fire sprinklers installation | 1835 | 15.1835 | 15.1825 | FS | 0 | 8
15 | Duct hangers and supports installation | 1840 | 15.1840 | 15.1845 | FS | 0 | 8
15 | Supply Ducts installation | 1845 | 15.1845 | 15.1860 | FS | 0 | 14
15 | Fresh Air Ducts installation | 1850 | 15.1850 | 15.1855 | FS | 0 | 6
15 | Smoke Ducts installation | 1855 | 15.1855 | 15.2080 | FS | 0 | 6
15 | Exhaust Ducts installation | 1860 | 15.1860 | 15.1850 | FS | 0 | 8
15 | Insulation works of supply ducts | 1865 | 15.1865 | 15.1890 | FS | 0 | 10
15 | Fresh air Fans installation | 1870 | 15.1870 | 16.2240 | FS | 0 | 8
15 | HVAC Sleeves and boxes | 1875 | 15.1875 |  |  |  | 6
15 | Fan Coil System - AC pipes installation | 1880 | 15.1880 | 09.1455 | FS | 0 | 10
15 | Fan Coil System - Drain pipes installation | 1885 | 15.1885 | 15.1910 | SS | 0 | 4
15 | Fan Coil System - Indoor units installation | 1890 | 15.1890 | 15.1915 | FS | 0 | 12
15 | Fan Coil System - External units installation | 1895 | 15.1895 | 15.1920 | FS | 0 | 12
15 | Fan Coil System - Connection of ducts | 1900 | 15.1900 | 09.1455 | FS | 0 | 4
15 | Air Handling System - AC pipes installation | 1905 | 15.1905 | 09.1455 | FS | 0 | 8
15 | Air Handling System - Drain pipes installation | 1910 | 15.1910 | 09.1455 | FS | 0 | 4
15 | Air Handling System - Indoor units installation | 1915 | 15.1915 | 15.1950 | FS | 0 | 12
15 | Air Handling System - External units installation | 1920 | 15.1920 | 15.1965 | FS | 0 | 12
15 | Air Handling System - Connection of ducts | 1925 | 15.1925 | 09.1455 | FS | 0 | 6
15 | Split Unit System - AC pipes installation | 1930 | 15.1930 |  |  |  | 2
15 | Split Unit System - Drain pipes installation | 1935 | 15.1935 |  |  |  | 2
15 | Split Unit System - Indoor units installation | 1940 | 15.1940 |  |  |  | 2
15 | Split Unit System - External units installation | 1945 | 15.1945 |  |  |  | 3
15 | Air Diffusers Installation | 1950 | 15.1950 | 09.1445 | FS | 0 | 12
15 | Air Curtain installation | 1955 | 15.1955 |  |  |  | 3
15 | Smoke Fans installation | 1960 | 15.1960 | 15.1970 | FS | 0 | 8
15 | Exhaust Fans installation | 1965 | 15.1965 | 15.1960 | FS | 0 | 8
15 | Presurrized Fans installation | 1970 | 15.1970 | 15.1870 | FS | 0 | 6
15 | BMS - Electrical first fix | 1975 | 15.1975 |  |  |  | 7
15 | BMS - Cables and Wires installation | 1980 | 15.1980 |  |  |  | 12
15 | BMS - DDC , Server , and Control units installation | 1985 | 15.1985 |  |  |  | 14
15 | Manholes Installation | 1990 | 15.1990 | 16.2225 | FS | 0 | 10
15 | FM 200 System - Pipes Installation | 1995 | 15.1995 | 15.2000 | FS | 0 | 6
15 | FM 200 System - Cylinders installation | 2000 | 15.2000 | 09.1445 | FS | 0 | 8
15 | FM 200 System - Nozzles installation | 2005 | 15.2005 | 15.2000 | FS | 0 | 6
15 | Valves Box Installation | 2010 | 15.2010 |  |  |  | 4
15 | Air Curtain installation | 2015 | 15.2015 |  |  |  | 3
15 | Smoke Fans installation | 2020 | 15.2020 |  |  |  | 8
15 | Exhaust Fans installation | 2025 | 15.2025 |  |  |  | 8
15 | Presurrized Fans installation | 2030 | 15.2030 |  |  |  | 6
15 | BMS - Electrical first fix | 2035 | 15.2035 |  |  |  | 7
15 | BMS - Cables and Wires installation | 2040 | 15.2040 |  |  |  | 12
15 | BMS - DDC , Server , and Control units installation | 2045 | 15.2045 |  |  |  | 14
15 | Manholes Installation | 2050 | 15.2050 |  |  |  | 10
15 | FM 200 System - Pipes Installation | 2055 | 15.2055 |  |  |  | 6
15 | FM 200 System - Cylinders installation | 2060 | 15.2060 |  |  |  | 8
15 | FM 200 System - Nozzles installation | 2065 | 15.2065 |  |  |  | 6
16 | Data and Telephone Cables installation | 2070 | 16.2070 | 16.2155 | FS | 0 | 8
16 | Low Current Cables installation (FA,AV,CCTV,MATV,ACC,PA) | 2075 | 16.2075 | 16.2150 | FS | 0 | 12
15 | Presurrized Ducts installation | 2080 | 15.2080 | 09.1455 | FS | 0 | 6
15 | Window/wall Mounted Exhaust Fans installation | 2085 | 15.2085 | 09.1445 | FS | 0 | 4
16 | Electrical conduits and boxes in concrete slab | 2090 | 16.2090 | 16.2100 | FS | 0 | 4
16 | Chipping and cutting in walls for electrical counduits and boxes | 2095 | 16.2095 | 16.2100 | FS | 0 | 12
16 | Installing electrical conduits & Boxes in walls / Ceiling | 2100 | 16.2100 | 09.1420 | FS | 0 | 6
16 | Installing electrical boxes in walls | 2105 | 16.2105 |  |  |  | 12
16 | Installing electrical conduits and boxes in floors | 2110 | 16.2110 | 16.2125 | FS | 0 | 4
16 | Installing cable tray supports and hangers | 2115 | 16.2115 | 16.2120 | FS | 0 | 8
16 | Installing cable tray | 2120 | 16.2120 | 16.2130 | FS | 0 | 8
16 | Wires installation | 2125 | 16.2125 | 16.2145 | FS | 0 | 16
16 | Power Cables installation | 2130 | 16.2130 | 16.2135 | FS | 0 | 6
16 | Distribution board installation and termination | 2135 | 16.2135 | 16.2230 | FF | 0 | 16
16 | Lighting fixtures installation | 2140 | 16.2140 | 16.2135 | FS | 0 | 14
16 | Sockets and Switches installation | 2145 | 16.2145 | 16.2155 | FS | 0 | 12
16 | Fire alarm system installation | 2150 | 16.2150 | 16.2135 | FS | 0 | 6
16 | Telephone and Data system installation | 2155 | 16.2155 | 16.2135 | FF | 0 | 6
16 | MATV System installation | 2160 | 16.2160 | 16.2165 | FF | 0 | 4
16 | Audiovisual system installation | 2165 | 16.2165 | 16.2170 | FF | 0 | 6
16 | CCTV system installation | 2170 | 16.2170 | 16.2250 | FF | 0 | 8
16 | PA System installation | 2175 | 16.2175 |  |  |  | 10
16 | UPS installation | 2180 | 16.2180 | 16.2160 | FF | 0 | 6
16 | Generator installation | 2185 | 16.2185 |  |  |  | 3
16 | Transformer installation | 2190 | 16.2190 |  |  |  | 3
16 | RMU installation | 2195 | 16.2195 |  |  |  | 3
16 | ATS installation | 2200 | 16.2200 |  |  |  | 3
16 | Capacitor bank installation | 2205 | 16.2205 |  |  |  | 3
16 | Switch-gear installation | 2210 | 16.2210 |  |  |  | 3
16 | Main distribution board | 2215 | 16.2215 |  |  |  | 3
16 | Earthing system-cables from RC elements to outside building | 2220 | 16.2220 | 07.1310 | FS | 0 | 4
16 | Earthing system-Installing and Connecting Ground Rods | 2225 | 16.2225 | 16.2230 | FS | 0 | 6
16 | Earthing system-Connecting ground network to distribution board | 2230 | 16.2230 | 16.2245 | FS | 0 | 10
16 | Lightning System-Cable from Roof to Ground | 2235 | 16.2235 | 16.2245 | FS | 0 | 8
16 | Lightning System-Air terminal devices installation | 2240 | 16.2240 |  |  |  | 8
16 | Lightning System-Connection to ground network | 2245 | 16.2245 |  |  |  | 10
16 | Access Control System | 2250 | 16.2250 | 16.2155 | FS | 0 | 6
16 | Fire Alarm Main Panel Board | 2255 | 16.2255 | 16.2155 | FF | 0 | 10